**DATE: Wednesday, April 25, 2018**

**TIME: 3:00-5:00 p.m.**

**LOCATION: Peoria City/County Health Department, Room 125**

1. Introductions (all)
2. Recap/Reminders (Melissa)
* All objectives need to be addressed in the tasks of each group
* Please specify the target audience for your tasks
* Team leads or co-leads still need to be identified for the public health group
* Keep the timeline in mind- these objectives go through 2019
* There has been some overlap between groups (FLASH for example) need to determine which group will cover
* Prioritization- what is realistic for this year, what do we have the capacity, time and resources to complete?
* Additional work may be necessary in between RHW meetings
1. Group work
* The 4 Teams (Behavioral and Biomedical, public health, Social marketing and structural) worked on their action plans.
1. Report out
	1. **Behavioral and Biomedical**: This is the second year for GYT events. Planning continues for the PREP event on May 16th. Decided the FLASH will go to the public health group. Comprehensive sex ed for the community will go to structural.
	2. **Public health:** co- leads have been assigned: Dana and Dr. Na’allah. There is a potential grant to provide LARC training in fall 2018. Discussion on prescription medication costs. Holly said Walmart offers birth control pills for $9 if not covered by your insurance. Barb said the website goodrx.com identifies coupons and the least expensive place to go for prescriptions. It has been decided that Task 6 will move to behavioral and biomedical.
	3. **Social Marketing:** Beth researched campaigns. Mentioned that kids like quizzes. In order to run a campaign, it would be ideal to have a designated person for twitter, blogs, etc. It was discussed that kids aren’t using facebook as much and we need to look at Snapchat and Twitter instead. Talked about using youth advisory council or PRIDE team to help teach younger kids. Planned Parenthood is running a campaign, “my body. My story.”
	4. **Structural:** some things have already been completed, will add column to work plan for completed items. Trying to create standards on how providers are talking with youth. Jimena and Joyce have been meeting to review. Discussion about trying to get a spot during teachers institute days.
2. Next steps
* Update work plan
* Group meetings as needed

**Next Meeting: Wednesday, May 23, 2018**